# Milestone Tracker, Automated Extraction and Analysis of Timing-Based Paradata Features for Survey Quality Assurance

Student: Samuel Kaoma (2022016530) · Course: CSC 4004 · Supervisor: Mr. Mofya Phiri
Repository: https://github.com/Samuelkaoma-eng/SKACE-TIME-DATA (branch main)
Proposal date: 26 March 2026 · Last verified: 14 July 2026 (33/33 tests passing in a clean environment; robustness round on held-out seeds: precision 0.95 to 1.00, recall 0.84 to 1.00, all runs above the proposal thresholds)

Commit links use the short hash; full history is on the commits page.

## Work Plan Status

| # | Phase (Proposal §6) | Planned Weeks | Status | Evidence and commits |
| --- | --- | --- | --- | --- |
| 1 | Proposal and Planning | 1 to 2 | Done | docs/deliverables/SAMUEL KAOMA 2022016530 V4.pdf (submitted proposal, 26 March 2026); source files docs/Samuel_Kaoma 2022016530_para data proposal.docx, docs/revised_proposal.md |
| 2 | Literature Review and Feature Cataloguing | 3 to 7 | Done | Proposal §2 (Tables 1 to 3, 40-feature catalogue); docs/feature_documentation.md, commits 37ae029 (first version), cad8b7a (final) |
| 3 | System Design | 8 to 9 | Done | Modular pipeline in src/: parsers, common intermediate representation, features, validation, controller; commits fe89e7f (skeleton), 37ae029 (architecture) |
| 4 | Parser Development (SurveyCTO + ODK) | 10 to 13 | Done | src/parsers/, unit tests in tests/test_parsers.py, commits 37ae029 (both parsers), 54ff5c7 (mixed-file handling), c82fd96 (timestamp parsing repair) |
| 5 | Feature Extraction Implementation (30 to 50 features) | 14 to 18 | Done | All 40 catalogued features (Q/S/V/T) in src/features/; tests in tests/test_features.py, commits 37ae029 (initial modules), 96f44db (full 40 with thesis alignment), 36ce869 (granular question/section exports) |
| 6 | Anomaly Detection (IQR + rule-based) | 19 to 21 | Done | src/validation/anomaly_detector.py, config in detector_config.py, commits 2f91436, 96f44db (detector), 84cae63 (config wiring), 7bb265d (de-tuning + elevated-pause rule) |
| 7 | Midway Evaluation (supervisor checkpoint) | 22 | Done | Week 16 progress report delivered: docs/progress_report_week16.md and docs/deliverables/Progress_Report_Week16.docx |
| 8 | Synthetic Dataset Generation and Validation | 23 to 26 | Done | Generator tests/test_adversarial.py + tests/generate_benchmark_datasets.py; canonical labelled datasets in data/synthetic_datasets/ (mirrored in docs/deliverables/Synthetic_Validation_Datasets/), commits 0d399cb (validation suite), 6716ab7 (labelled evaluation), 42bae73 (benchmark generator), 7bb265d (realism upgrade + held-out robustness round: output/robustness_validation/robustness_summary.md, reproducible via scripts/run_robustness_validation.py) |
| 9 | Output and Documentation | 27 to 29 | Done | docs/feature_documentation.md, docs/paradata_format_guide.md, structured outputs in output/, commits 5370dac, cad8b7a |
| 10 | Final Report Writing (5,000 to 7,000 words) | 30 to 31 | Done | docs/deliverables/SAMUEL KAOMA 2022016530 Final Report.docx (Harvard referencing, includes the reconciled robustness results); markdown source in report/final_academic_report.md |
| 11 | Final Submission | 32 | Ready | Submission package prepared and verified in a clean environment on 14 July 2026: code, datasets, Word deliverables in docs/deliverables/, presentation docs/deliverables/Kaoma_Paradata_Presentation.pptx, and this tracker |

## Expected Outcomes (Proposal §4), Deliverable Check

| Deliverable | Status | Location |
| --- | --- | --- |
| Python feature library, 30 to 50 features, documented | Done (40 features) | src/features/; docs/feature_documentation.md, docs/feature_library_usage.md, Word copies in docs/deliverables/ |
| Paradata format guide (SurveyCTO + ODK) | Done | docs/paradata_format_guide.md, docs/deliverables/Paradata_Format_Guide.docx |
| Synthetic validation dataset with injected anomalies + labels | Done | data/synthetic_datasets/, mirrored in docs/deliverables/Synthetic_Validation_Datasets/; ready-to-run sample data/surveycto.csv, data/odk.csv, data/ground_truth_labels.csv (seed 42) |
| Validation report (precision, recall, effect sizes) | Done | docs/validation_report.md, docs/deliverables/Validation_Report.docx, evidence in output/robustness_validation/robustness_summary.md |
| Final paper 5,000 to 7,000 words | Done | docs/deliverables/SAMUEL KAOMA 2022016530 Final Report.docx; source report/final_academic_report.md |
| Structured output dataset + statistical summaries + visualizations | Done | output/: feature datasets, anomaly reports, metrics, synthetic_metrics_overview.png, synthetic_detection_by_type.png |
| AI Usage Log appendix (Proposal §9.4) | Done (maintained live) | docs/ai_usage_log.md, docs/deliverables/AI_Usage_Log.docx |

## Progress Review Checkpoints

Counting from the proposal (Week 1 ≈ 23 March 2026):

- Week 8 review ≈ mid-May 2026. The review itself was missed; a reconstructed checkpoint summary describing the project as it stood then: docs/progress_report_week08.md and docs/deliverables/Progress_Report_Week08.docx.

- Week 16 review ≈ 6 to 12 July 2026. Progress report: docs/progress_report_week16.md and docs/deliverables/Progress_Report_Week16.docx.

- Week 24 review ≈ early September 2026. Prepared summary: docs/progress_report_week24.md and docs/deliverables/Progress_Report_Week24.docx.